## meeting points
1 | Client Module
1 | Create client profile | demographics, appointment dates (dynamic) | role -> salesman
2 | Contract information | once client sings a contract
3 | Service provider list | partners
4 | Document upload | 4 document types
5 | Call | verify from clients -> valid or cancel | role -> admin
6 | Status Update | 4 status
7 | Dynamic contract
8 | Static contract
9 | statistics
10 | dashboard
11 | Agency CRUD

## estimation
S.No. | Tasks | Development effort (days) | Testing & Misc. efforts (days) | Total effort (days)
1 | Document upload option in dynamic forms | 8 | 1.6 | 9.6
2 | Agency CRUD | 4 | 0.8 | 4.8
3 | Option to tag agency to the client/contract | 1 | 0.2 | 1.2
4 | Filter contracts/clients per agency | 4 | 0.8 | 4.8
5 | Appointment calendar for agency director | 4 | 0.8 | 4.8
6 | Statistics | 4 | 0.8 | 4.8
7 | Dashboard | 4 | 0.8 | 4.8
8 | Ranking | 3 | 0.6 | 3.6
9 | Revenue | 3 | 0.6 | 3.6
| Total | 35 | 7 | 42
Incase they need dynamic formula management for revenue and ranking then:
10 | dynamic ranking and revenue formula | 10 | 3 | 13
| Total | 45 | 10 | 55