## Sheet1
Changes and bug fixes report by client					Bug	Change Minor|Major		Change Apply
size of canvas need to be adjust to the screen					X		done
default position of the actuator needs to move slightly up and in the canvas					X		done
Market segment names needs to be in a similar comment box as we have the names of the products					X	pending
When only actuator is selected, allow to go more closer to the actuator. (Same as when the can is selected)					X	pending
When the can is selected, allow to go a little bit further away, so the zoom out will work for all can size, especially the big ones (ex. 52x244)					X	pending
We still have to issues with the labels					X			pending
Please sort all cans from the smallest to the biggest. Some are randomly selected and some are sorted from the biggest to the smallest					X		done
When Shark 65 or 57 are selected, you can still click the Aluminium button, This needs to be greyed (inactive) as there are no aluminium can for them.					X	pending
Linroc 1 and 2 needs to be zoomed out when selected					X	done
Linroc 1 lever to be metallic like the mounting cup					X			done
Playboy is only compatible with TP cans of 49 x 151, 49x 185 and 49 x 222 – no other cans.					X	pending
For some reason, the default colour of the cans is with a hex code of ff4500 even if it is shown as white. Change it to white hex code.					X		done
Change default blue (fingerpad…) hex code to #002c5b (This is lindal’s brand colour)					X		done
When selecting Top, the position of the label is altered, as well as the movement of the can					X			pending
sometime the TP can button appears selected but we see the icons of aluminium cans					X			pending
By default can we have the label present in the artwork page. By clicking on the x, the user can delete the default lindal label and see a blank can without label. He can also apply a new label.					X	pending
The overcap is not transaparent as I selected and The position of the controller is not the same (bottom right)					X			pending
When actuator shown alone : don’t show either the valve body nor the mounting cup. It should be loaded with can					X	done
Can selection icons : Please replace by the attached icons in the folder called “LG - ALU & TP Icons Pack_2”. Sorry but the one provided earlier where wrong.					X		done
When Users are saving, this should not send them an email but Save their configuration into their login so they can open it later if they wish. They should be able to give a name to the configuration they are saving.					X	pending
There should be a share button which will open a form to add email address of the recipient. Then both the recipient and the user will receive the read only link. The shared configuration will be saved automatically in Users login					X	pending

Can type Icon (Menu) : Please replace the “Can Type” icon by the ones attached in the folder called “Navigation”					X		done